Appendix I: Quality Checklists WP1-8

Quality Checklist for WP 1, led by P1, chair Ivana Perković

| Quality Checklist Parameters: WP 1 Preparation and analysis |
| --- |
| Tasks | Assumptions & risks | Deliverables | Due Date* | Indicators of progress | Target groups | QAG member** |
| 1. 1 Analysis, review of national and comparative analysis of national and EU programmes 1. 2. Study visits to EU HEIs 1. 3. Defining outcomes and competences 1. 4. Modernization of study programmes, adoption of reformed study programmes 1. 5. Design and accreditation of new study programmes | A: Availability of staff members with respective qualifications A: Efficient management of the project at regional and international level A: Commitment of the management of HMEI A: Self-financing of some activities A: Motivation to implement project results A: Knowledge and experience in project implementation A: Risk recognizing and prevention R: Political and economic instability in the region R: Problems with existing networks R: Government changes R: Inertia of the stakeholders | 1. 1. Current national study programmes analyzed, reviewed and compared with similar EU programmes | 15/06/2019 | - 1 international institutional review/need analysis of Serbian curricula regarding project aims; - 3 comparative reports; | Teaching staff Students Administrative staff Technical staff | Martin Prchal Nynke van Ketel Elsa Ferreira |
|  |  | 1. 2. Three study visits to EU HEIs completed | 14/05/2019 | - 3 study visits to EU HE partner institutions – review of EU study programmes dealing with music in digital environment (study visit to P5 and P6) and entrepreneurship (visit to P4); | Teaching staff Administrative staff Technical staff | Martin Prchal Nynke van Ketel Elsa Ferreira |
|  |  | 1. 3. Learning outcomes and competences defined | 01/07/2019 | - 1 report on stakeholder analysis – defining learning outcomes and competences; | Teaching staff Other | Martin Prchal Nynke van Ketel Elsa Ferreira |
|  |  | 1.4. Current study programmes modernized and adopted | 15/09/2019 | - at least 9 study programmes modernized; - at least 8 new courses on musical entrepreneurship and music-related digital technology developed and introduced into curricula at BA and MA; | Teaching staff Students Administrative staff | Martin Prchal Nynke van Ketel Elsa Ferreira |
|  |  | 1.5. New study programs designed and accredited | 01/10/2020 | - one new master study programme developed, accredited and introduced; | Teaching staff Students Administrative staff Technical staff | Martin Prchal Nynke van Ketel Elsa Ferreira |

* According to the Adjusted Project Work Plan of PMP;

** QAG member responsible for internal quality control and monitoring;

Quality Checklist for WP 2, led by P1, chair Milena Stanišić

| Quality Checklist Parameters: WP 2 Upgrading of methodology |
| --- |
| Tasks | Assumptions & risks | Deliverables | Due date* | Indicators of progress | Target groups | QAG member** |
| 2.1. Creation of equipment purchase plan 2.2. Purchase of hardware 2.3. Purchase of software 2.4. Development of adequate digital infrastructure 2.5. Installation and set up equipment 2.6. Creation of distance learning platform | A: Competent staff with adequate skills A: Existing music and media laboratories at P2 and P3 R: Tender procedures slow and complicated R: Delay of delivery of specialized equipment R: Difficulties in adjusting the needs of each HEI to shared distance learning platform | 2.1. Equipment purchase planned written; Tendering procedure realized; | 15/04/2019 | - equipment purchase plan written; - tendering procedure realized; | Teaching staff Administrative staff Technical staff | Sanela Nikolic |
|  |  | 2.2. Hardware purchased | 14/07/2019 | - hardware and software equipment purchased and digital infrastructure developed at P1-3 (new music digital laboratory developed at P1, music labs at P2 and P3 modernized with hardware /computers, sound cards, loudspeakers, headphones, UPS, SWITCH/, and software /Sibelius, Cubase, Finale/, piano, etc.); | Teaching staff Students Administrative staff Technical staff | Sanela Nikolic |
|  |  | 2.3. Software purchased | 14/07/2019 |  |  | Sanela Nikolic |
|  |  | 2.4. Adequate digital infrastructure developed | 30/09/2019 |  |  | Sanela Nikolic |
|  |  | 2.5. Equipment installed and set up | 15/01/2020 new date: June 1, 2021 | EQUIPMENT: computers X 23; microphones, stands, 20; speakers, amplifiers 10; printers, scanners 7; software X 41; interactive board X 3; audio recorders X 6; headphones X 17; sound cards X 12; UPS, SWITCH, router X3; audio mixer; monitors X 8; bundle X 13; digital camera X 3; piano X 1, electric piano X 3 | Teaching staff Students Administrative staff Technical staff | Sanela Nikolic |
|  |  | 2.6. Distance learning platform created | 14/03/2020 | - Moodle platform adjusted and implemented at 3 national HEIs (P1-3); - LoLa system used for distance music performance; | Teaching staff Students Administrative staff Technical staff | Paulina Gut |

* According to the Adjusted Project Work Plan of PMP;

** QAG member responsible for internal quality control and monitoring.

Quality Checklist for WP 3, led by P2, chair Ira Prodanov

| Quality Checklist Parameters: WP 3 Staff training and development of teaching resources |
| --- |
| Tasks | Assumptions & risks | Deliverables | Due date* | Indicators of progress | Target groups | QAG member** |
| 3.1. Training of teachers for new academic courses 3.2. Training of teachers and staff for distance learning and LoLa equipment 3.3. Preparation and publication of teaching materials 3.4. Preparation of on-line courses | A: Availability of staff members with respective qualifications A: Efficient management of the project at regional and international level A: Self-financing of some activities A: Motivation to implement project results A: Knowledge and experience in project implementation A: Risk recognizing and prevention | 3.1. Teachers trained for curricular changes and LLL courses. | 15/12/2019 new date: November 1, 2020 | - at least 36 teachers from P1-3 trained at EU institutions (P4 provided training for music entrepreneurship /Entrepreneurship and project management; Performance and Communication/, P5 and P6 provided training for digital empowerment of existing study programmes and new master programme /Digital marketing, Audio Software, Music and computers, Audio fundamentals for recording, Creative music production skills, Sound directing fundamentals, etc./); | Teaching staff | Martin Prchal Nynke van Ketel Elsa Ferreira |
|  |  | 3.2. Teachers and staff trained for distance learning and LOLA equipment | 30/10/2020 February 1, 2021 | - at least 18 teachers and 10 staff members from P1-3 trained for distance learning and LoLa system at national HEIs; - 2 two-day courses organized at each of national HEIs; | Teaching staff Technical staff | Martin Prchal Nynke van Ketel Elsa Ferreira |
|  |  | 3.3. Teaching materials developed and published | 31/03/2021 | - at least 8 new teaching manuals (textbooks or online manuals) developed and published for reformed curricula; - at least 5 new teaching manuals (textbooks or online manuals) developed and published for the new master study programme; | Teaching staff Technical staff | Martin Prchal Nynke van Ketel Elsa Ferreira |
|  |  | 3.4. On-line courses prepared | 14/09/2021 | - at least 1 new online course prepared at each national HEI. | Teaching staff Technical staff | Martin Prchal Nynke van Ketel Elsa Ferreira |

* According to the Adjusted Project Work Plan of PMP;

** QAG member responsible for internal quality control and monitoring.

Quality Checklist for WP 4, led by P2, chair Olivera Gračanin

| Quality Checklist Parameters: WP 4 Implementation of reformed and new study programs |
| --- |
| Tasks | Assumptions & risks | Deliverables | Due date* | Indicators of progress | Target groups | QAG member** |
| 4.1. Enrollment of students to modernized study programmes 4.2. Enrollment of students to new master programme 4.3. Implementation of modernized and new study programmes 4.4. Implementation of on-line courses 4.5. Realization of student placements | A: Teaching staff and students familiar with the project A: Availability of staff members with respective qualifications R: Reluctance of teaching staff to digital technologies R: Lack of possibility to choose the best candidates at entrance exams | 4.1. Students enrolled to modernized study programmes | 30/09/2021 | - more than 300 students; | Teaching staff Students Administrative staff Librarians | Aleksandar Mrdjan |
|  |  | 4.2. Students enrolled to the new master programme | 30/09/2021 | - 10 students enrolled per year; | Teaching staff Students Administrative staff Librarians | Aleksandar Mrdjan |
|  |  | 4.3. Modernized and new study programmes implemented | 14/01/2022 | - at least 8 new courses on musical entrepreneurship and music-related digital technology developed and introduced into curricula at BA and MA; - one new master study programme developed, accredited and introduced; - at least 9 study programmes modernized; - new learning outcomes developed (problem solving, music project writing, communication and planning skills, fundamental knowledge of digital electronics and contemporary audio recording and processing software, understanding of on-line resources for music teaching, research and performance, expanded cultural understanding through musical study, etc.); | Teaching staff Students Librarians | Sanela Nikolic |
|  |  | 4.4. On-line courses implemented; | 14/01/2022 | - at least 3 online courses developed and implemented during the project; | Teaching staff Students Technical staff | Sanela Nikolic |
|  |  | 4.5. Student placements realized; | 31/05/2021 | - more than 20 student placements realized in IT and media companies; | Teaching staff Students Administrative staff Technical staff | Aleksandar Mrdjan |

* According to the Adjusted Project Work Plan of PMP;

** QAG member responsible for internal quality control and monitoring.

Quality Checklist for WP 5, led by P3, chair Biljana Mandić

| Quality Checklist Parameters: WP 5 LLL courses |
| --- |
| Tasks | Assumptions & risks | Deliverables | Due date* | Indicators of progress | Target groups | QAG member** |
| 5.1. Design and accreditation of LLL courses 5.2. Preparation of teaching and learning materials for LLL courses 5.3. Implementation of LLL courses | A: Lifelong Learning Centre fully operating at P3 A: National HEIs have solid experience in LLL courses A: By now many LLL teaching staff is already involved in courses at national HEIs covering the same topics as LLLs R: Deadline extensions and slow accreditation procedure at national Institute for the Promotion of Education | 5.1. LLL courses designed and accredited | 31/10/2020 new date: November 1, 2021 | - at least 10 LLL courses developed and implemented (Digital technologies in music education, On-line resources for music performance, Mobile apps for music teachers, Digital resources for Music history teachers, etc. accredited by the national Institute for the Promotion of Education); | Teaching staff Trainees Administrative staff Technical staff | Paulina Gut |
|  |  | 5.2. Teaching and learning material for LLL courses prepared | 30/06/2021 | - learning materials/manuals prepared by teachers or LLL trainers in printed or electronic form; | Teaching staff Technical staff | Paulina Gut |
|  |  | 5.3. LLL courses implemented | 14/01/2022 | - at least 500 participants attended courses, organized in traditional classroom or via distance learning; | Teaching staff Trainees Technical staff | Paulina Gut |

* According to the Adjusted Project Work Plan of PMP;

** QAG member responsible for internal quality control and monitoring.

Quality Checklist for WP 6, led by P3, Vladimir Blagojević

| Quality Checklist Parameters: WP 6 Quality Control and Monitoring |
| --- |
| Tasks | Assumptions & risks | Deliverables | Due date* | Indicators of progress | Target groups | QAG member** |
| 6.1. Quality Assurance Group 6.2. Project Quality Action Plan 6.3. Internal quality procedures 6.4 External quality procedures | A: Availability of staff members with respective qualifications A: Knowledge and experience in project implementation A: Risk recognizing and prevention | 6.1. Quality assurance group established | 31/12/2021 | - number and quality of accepted reports on project implementation; | Teaching staff Students Administrative staff | Vladimir Blagojevic |
|  |  | 6. 2. Quality action plan developed | 30/11/2019 |  | Teaching staff Students Administrative staff Administrative staff | Vladimir Blagojevic |
|  |  | 6. 3. Internal quality procedures implemented | 14/01/2022 |  | Teaching staff Students Trainees Administrative staff Technical staff | Vladimir Blagojevic |
|  |  | 6. 4. External quality procedures implemented | 01/10/2021 |  | Teaching staff Students Trainees Administrative staff Technical staff | Vladimir Blagojevic |

* According to the Adjusted Project Work Plan of PMP;

** QAG member responsible for internal quality control and monitoring.

Quality Checklist WP 7, led by P2, chair Olivera Gračanin

| Quality Checklist Parameters: WP 7 Dissemination and exploitation |
| --- |
| Tasks | Ass. & risks | Deliverables | Due date* | Indicators of progress | Target groups | QAG** |
| 7.1.The dissemination and exploitation plan 7.2. Project web site and social media 7.3. Academic and financial sustainability plan 7.4. Preparation of promotional material 7.5. Project promotional activities 7.6. Realization of public student projects 7.7. Realization of public debate in Novi Sad | A: Availability of staff members with respective qualifications A: Risk recognizing and prevention | 7.1.The dissemination and exploitation plan developed | 30/06/2019 | - dissemination and exploitation plan developed; | Teaching staff Students Trainees Administrative staff Technical staff Librarians Other | Paulina Gut |
|  |  | 7.2. Project web site set up, social media engaged | 14/01/2022 | - project web site created (containing useful information, guides and teaching material, as well as partners’ area with documents, reports, etc.) with video repository designed to provide video/audio clips from various events; - project logo created and used in newsletters, brochures and other communication and dissemination documents; - project banner (web banner and roll up) created to attract the attention of visitors of different events and website visitors. - all partners included a page/section related to the project on their website; - main events, lectures and music performances from P1-P3 recorded, edited and shared publicly on the project YouTube channel and web site video depository; - project news disseminated through social networks; |  | Paulina Gut |
|  |  | 7.3. Academic and financial sustainability plan created | 14/01/2021 | - academic and financial sustainability plan created; | Teaching staff Administrative staff | Paulina Gut |
|  |  | 7.4. Promotional material prepared | 30/11/2021 | - printed and digital promotional material prepared; - periodic newsletter sent to the network of participants and stakeholders; | as to 7.1. | Paulina Gut |
|  |  | 7.5. Promotional activities held | 14/01/2022 | - audience informed on project results through regular concerts and public performances at the greatest concert venues in Serbia; - other events, conferences, workshops, international information forums and media used for dissemination of information; - RTS partnership used for project promotion; | as to 7.1. except Librarians | Paulina Gut |
|  |  | 7.6. Student projects made public | 02/10/2021 | - 15 student projects made public using digital technologies; | Teaching staff Students Administrative staff Technical staff Librarians | Aleksandar Mrdjan |
|  |  | 7.7. Public debate in Novi Sad, European capital of Culture 2021 held | 16/10/2021 | - public debate in Novi Sad, European cultural capital 2021 organized in order to achieve wider impact with governmental and civil society participants; | Teaching staff Students Trainees Administrative staff Technical staff Librarians Other | Aleksandar Mrdjan |

* According to the Adjusted Project Work Plan of PMP;

** QAG member responsible for internal quality control and monitoring.

Quality Checklist for WP 8, led by P1, chair Ivana Perković

| Quality Checklist Parameters WP 8 Management of the project |
| --- |
| Tasks | Assumptions & risks | Deliverables | Due date* | Indicators of progress | Target groups | QAG member** |
| 8.1. Kick-off meeting preparation and realization 8.2. Project management board establishment 8.3. Project management plan 8.4. Day-to-day coordination activities | Keeping the timelines and agreed critical paths Changing priorities within the partner institutions External risks: government regulations, changes in economic conditions, fluctuation of local currencies. | 8.1. Kick off meeting held and management structure established | 21-22/02/2019 | - project management board established; - project management plan defined; - project partners coordinated; - communication and report mechanisms established; - project realized in accordance with Project Management Plan WPs tasks, reporting schedule, defined timetables, reporting mechanisms and financial guidelines; | Teaching staff Administrative staff Technical staff | Sanela Nikolic |
|  |  | 8.2. Project management board established | 30/10/2021 |  | Teaching staff Administrative staff Technical staff Other | Sanela Nikolic |
|  |  | 8.3. Project management plan defined | 31/03/2019 |  | Teaching staff Administrative staff Technical staff | Sanela Nikolic |
|  |  | 8. 4. Coordination | 14/01/2022 |  | Teaching staff Administrative staff Technical staff | Sanela Nikolic |

* According to the Adjusted Project Work Plan of PMP;

** QAG member responsible for internal quality control and monitoring.