## Project Timeline
PROJECT TIMELINE
PROJECT TITLE |  | Enhancing the digital competencies and entrepreneurship skills of academic musicians in Serbia for culturally more engaged society – DEMUSIS
PROJECT MANAGER |  | Ivana Perković |  | START DATE | [6 empty] | 2019-01-15
WP |  |  | ACTIVITY | Y1 | [11 empty] | Y2 | [11 empty] | Y3
| PROJECT MONTH: |  |  | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12
WP 1 | Preparation and Analysis |  | WP 1.1.Current national study programmes analyzed, reviewed and compared with similar EU programmes | bar: Y1 M2 to Y2 M5
WP 1.2. Study visits to EU Higher education institutions | bar: Y1 M2 to Y1 M12
WP 1.3. Learning outcomes and competences defined | bar: Y1 M2 to Y1 M6
WP 1.4. Current study programmes modernized and adopted | bar: Y1 M2 to Y1 M9
WP 1.5. New study programs designed and accredited
WP 2 | Upgrading of methodology |  | WP 2.1 Equipment purchase plan | bar: Y1 M2 to Y1 M6
WP 2.2. Hardware purchase | bar: Y1 M6 to Y2 M9
WP 2.3 Software purchase | bar: Y1 M6 to Y2 M9
WP 2.4 Development of adequate infrastructure | bar: Y1 M8 to Y1 M12
WP 2.5 Equipment installation and set-up | bar: Y1 M8 to Y2 M11
WP 2.6 Creation of distance learning platform | bar: Y1 M10 to Y3 M1
WP 3 | Staff training and development of teaching resources |  | WP 3.1 Teachers training for curricular changes and LLL courses | bar: Y2 M3 to Y3 M1
WP 3.2 Teacher and staff training for distance learning and LoLa equipment | bar: Y2 M2 to Y3 M1
WP 3.3 Teaching materials' development and publishing | bar: Y2 M2 to Y3 M3
WP 3.4 Preparation of online courses | bar: Y2 M2 to Y3 M9
WP 4 | Implementation of reformed and new study programs |  | WP 4.1 Student enrollment to modernized study program | bar: Y1 M9 to Y1 M10; Y2 M9 to Y2 M10; Y3 M9 to Y3 M10
WP 4.2 Student enrollment to new study programs | bar: Y2 M9 to Y2 M10; Y3 M9 to Y3 M10
WP 4.3 Implementation of modernized and new study programs | bar: Y1 M10 to Y3 M12
WP 4.4 Implementation of online courses | bar: Y2 M3 to Y3 M12
WP 4.5 Student placements | bar: Y3 M2 to Y3 M12
WP 5 | LLL courses development and implementation |  | WP 5.1 LLL courses design and accreditation | bar: Y2 M6 to Y3 M10
WP 5.2 Preparation of LLL courses learning materials | bar: Y3 M5 to Y3 M6
WP 5.3 Implementation of LLL courses | bar: Y3 M8 to Y3 M11
WP 6 | Quality control and monitoring |  | WP 6.1 Quality Assurance Group
WP 6.2 Project Quality Action Plan | bar: Y1 M4 to Y2 M2
WP 6.3 Internal Quality Procedures
WP 6.4 External Quality Procedures | bar: Y1 M4 to Y3 M11
WP 7 | Dissemination and exploitation plan |  | WP 7.1 Dissemination and exploitation plan | bar: Y1 M2 to Y2 M8
WP 7.2 Project website, social media engagemenet
WP 7.3 Academic and financial sustainability plan | bar: Y3 M11 to Y3 M12
WP 7.4 Preparation of promotional materials
WP 7.5 Promotional activities | bar: Y1 M1 to Y3 M12
WP 7.6 Student projects | bar: Y3 M4 to Y3 M8
WP 7.7 Public debate in Novi Sad, European Capital of Culture | bar: Y3 M5 to Y3 M11
WP 8 | Management |  | WP 8.1 Kick-off meeting | bar: Y1 M2
WP 8.2 Establishment of Project Management Board | bar: Y1 M2
WP 8.3 Project Management Plan | bar: Y1 M3 to Y1 M10
WP 8.3 Day-to-day coordination activities